## Instructions
SE Lab Assignment 1 Team Workbook
Smart Ticketing System (TVM) ¦ Sem 1_2627 ¦ One workbook per group, kept in your shared folder and in your GitHub repository
Purpose
This workbook is your group's working record for Lab Group Assignment 1. It contains the Clarification Q&A and the requirements (two deliverables you hand in as Excel or Word), plus trackers that show your process: who built what, the diagrams and their status, your Copilot prompts, your commits and your weekly progress. The lecturer reads it during the labs and replies in the green cells. Student self-marking and lecturer marking are on the Marking sheet. It supports, and does not replace, your official submission (the .docx report, readme.txt and the % contribution).
How to use it
1. Fill in the Team sheet first (3 to 5 students, % contribution totalling 100%).
2. Do the Clarification Q&A before you write the requirements. Every assumed answer should lead to a requirement ID.
3. Update the Artifact Tracker, Commit Log, AI Prompt Log and Progress Log every lab week. These show the process mark evidence.
4. Before submission, use the Consistency Check sheet, then self-mark on the Marking sheet. The lecturer marks in the green column.
Colour legend
Student input | Yellow fill, blue text
Lecturer input | Green fill, blue text
Calculated / fixed | Black text, no fill
Sheets in this workbook
Sheet | What it is for | Report section it feeds | When to fill in
Team | Members, roles, % contribution, commit counts | 1.3, 7 | Week 1
Clarification Q&A | Ambiguities, questions and assumed answers (Task 1, 5%) | 2.1 | Before requirements
Requirements | Functional, non-functional and domain requirements with measurable metrics (Task 2, 15%) | 2.2 | Phase 1
Use Cases | Use case register and description status (Task 3) | 3.1 | Phase 2
Artifact Tracker | Every deliverable: owner, tool, link, status, % done | All | Throughout
Consistency Check | Alignment of the diagrams and the code | 3.4 | Before submitting
AI Prompt Log | Copilot prompts, how the AI helped, how you validated (Task 9) | 5.2.2 | Throughout
Commit Log | Commits and pull requests per member per week | 5.2.1 | Weekly
Progress Log | Weekly plan, actual work, evidence and lecturer feedback | Process mark | Weekly
Marking | Self-mark and lecturer mark for the 10 tasks (100%) | – | End
Summary | Group result, QT2 points and individual marks | – | End

## Team
Team and Contribution
Group of 3 to 5 students. The % contribution of each member must total 100% and match your readme.txt.
Group name
GitHub repo
Group size | 1
Size check | Group must have 3 to 5 students
Members
Member | Name | Student ID | Role / main responsibility | % contribution | Commits (from Commit Log) | Check
Member 1
Member 2
Member 3
Member 4
Member 5 | [Student Name 5] | 524H0199 | UI/UX Touchscreen Mockups (4.1); UML Deployment Diagram (4.2.2); C# .NET 8 WinForms & MSSQL Demo (5.3) | 20% | 12 | OK
|  |  | Total contribution | 20%
|  |  | Check | Must total 100%
Contribution is the share of the whole project each member built, in agreement with the group. The lecturer may adjust it using the Git history, the pull requests and individual questions.

## Clarification Q&A
Clarification Q&A (Task 1, 5 marks)
Identify the ambiguities in the problem statement, ask the stakeholders, and give logical assumed answers to base your design on.
Q ID | Area | Ambiguity found in the problem statement | Clarifying question to the stakeholder | Stakeholder asked | Assumed answer (logical) | Rationale and impact on the design | Requirement ID | Status | Lecturer comment
Q01
Q02
Q03
Q04
Q05
Q06
Q07
Q08
Q09
Q10
Q11
Q12
Q13
Q14
Q15
Q16
Q17
Q18
Q19
Q20
Q21
Q22
Q23
Q24
Q25
|  | Questions written | 0
|  | Questions linked to a requirement | 0
|  | Areas covered | 0
Strong Q&A uncovers hidden complexity (timeouts, declined payments, refunds, printer or paper out, offline mode, fares). Aim for several different areas, not many questions on one topic.

## Requirements
Requirements Specification (Task 2, 15 marks)
Functional, Non-Functional and Domain requirements. Every NFR needs a measurable metric. Focus: reliability and response time.
ID | Requirement | Type | Category (NFR) | Measurable metric / fit criterion (NFR) | Measurement method | Priority | Use case | Source (Q ID) | Lecturer comment
| Functional requirements | 0
| Non-functional requirements | 0
| Domain requirements | 0
| NFRs without a measurable metric | 0
| Reliability NFRs (need at least 1) | 0
| Response-time NFRs (need at least 1) | 0
| Critical focus check | Check NFRs

## Use Cases
Use Case Register (Task 3)
One row per use case. Each needs a full description and appears in the use case diagram.
ID | Use case | Primary actor | Short description | Requirement IDs | Description written? | In activity / sequence diagram? | Owner (ID) | Lecturer comment
UC01
UC02
UC03
UC04
UC05
UC06
UC07
UC08
UC09
UC10
UC11
UC12

## Artifact Tracker
Artifact Tracker
Track every deliverable. Percent complete is calculated from the status.
Task | Artifact | Marks | Tool | Owner (ID) | File / link | Status | % complete | Lecturer comment
1 | Clarification Q&A (Excel) | 5
2 | Requirements Specification | 15
3 | Use case diagram | 5
3 | Use case descriptions | 5
4 | Activity diagram: buy a ticket | 5
4 | Activity diagram: payment gateways | 5
5 | Sequence diagram | 5
5 | State chart diagram | 5
5 | Class diagram | 5
6 | UI/UX wireframes or mockups | 5 | Figma / HTML5 SVG | 524H0199 | https://www.figma.com/design/chjKyWaJin2KMWQ9iaUzuP/TVM?node-id=0-1&t=MFddgbURntkb09Qw-1 | Done | 100%
7 | Architecture diagram | 5
7 | Deployment diagram | 5 | PlantUML / Graphviz | 524H0199 | deployment_diagram.png | Done | 100%
8 | VS forward engineering (model to code) | 4
8 | VS backward engineering (code to model) | 3
8 | VS Code Map | 3
9 | GitHub repository with collaboration history | 5
9 | Copilot prompt documentation | 5
10 | Demo: C# and MSSQL input form | 4 | VS 2022 / .NET 8 WinForms | 524H0199 | src/TvmDemo/Views/MainForm.cs | Done | 100%
10 | Demo: output report or success screen | 3 | VS 2022 / TicketPrinter.cs | 524H0199 | src/TvmDemo/Views/MainForm.cs (S05a) | Done | 100%
10 | Demo: database script and run instructions | 3 | MSSQL LocalDB & Express | 524H0199 | db/TvmDemo_Setup.sql | Done | 100%
– | Report .docx | 0
– | readme.txt | 0
– | % contribution of each member | 0
| Overall progress | 100%
| Artifacts done | 5 of 23
Marks column shows the weight of each task of the assignment (split across its artifacts for tracking only).

## Consistency Check
Model Consistency Check
Diagrams must be syntactically correct, logically sound and aligned with each other.
# | Check | Diagrams involved | Student | Lecturer | Notes
1 | Every use case in the diagram has a description, and every description is in the diagram | Use case diagram / descriptions
2 | Every step of the main flow appears in the activity diagram | Descriptions / activity
3 | Objects and messages in the sequence diagram exist as classes and methods in the class diagram | Sequence / class
4 | State names and transitions match the events in the sequence diagram | State chart / sequence
5 | Payment gateway steps match between both activity diagrams and the sequence diagram | Activity / sequence
6 | Requirement IDs are cited in the use cases | Requirements / use cases
7 | The class diagram matches the C# code from forward and backward engineering | Class / code
8 | The UI screens match the steps of the main flow | Wireframes / descriptions | Yes |  | Screens S01-S08 map 1:1 to UC01 main purchase flow, card/QR payment, ticket printing, and exception handlers
9 | The architecture and deployment diagrams show the same components | Architecture / deployment | Yes |  | Both diagrams represent TVM Kiosk, Display, TicketPrinter, CardReader, Central App Server, SQL Server, and Gateway APIs
10 | UML notation is correct (arrows, multiplicities, guards, swim lanes) | All diagrams

## AI Prompt Log
AI Prompt Log (Task 9)
Document each prompt to GitHub Copilot (or a similar tool), how it helped, and how you validated the generated code.
No. | Date | Student ID | Tool | Task / artifact | Prompt used | How the AI helped (boilerplate / logic / explanation) | Output used? | How we validated it (tests, code review, run) | Lecturer comment
1 | 2026-10-28 | 524H0199 | GitHub Copilot | Task 6 / UI/UX Design | Generate 10 touch-friendly TVM screens in SVG/WinForms layout (1280x800) with frosted glass aesthetic, bilingual EN/VI support, and WCAG AA contrast for metro ticketing kiosk. | Created glassmorphism token structure, color palettes (Navy, Blue, Teal, Success Green, Danger Red), and 64px touch target layouts for screens S01 to S08. | Kept | Validated with Chrome rendering, contrast checks (>= 4.5:1), and WinForms DPI scaling tests.
2 | 2026-10-29 | 524H0199 | GitHub Copilot | Task 7 / Deployment Diagram | Write PlantUML deployment diagram for smart ticketing TVM: 3 network boundaries (Station LAN, Operator Network, External Internet) with HTTPS/mTLS and PCI-DSS tokenization. | Generated PlantUML script specifying hardware peripherals, mTLS port 443 backend, and webhook callback security. | Kept | Rendered with Graphviz/PlantUML compiler to PNG, cross-checked against Section 1.1 architecture specification.
3 | 2026-10-29 | 524H0199 | GitHub Copilot | Task 10 / Demo C# & MSSQL | Implement TicketPrinter.cs to render ESC/POS style thermal paper ticket with 1D Code 128 barcode and Luhn-validated 16-digit TicketNumber in C# WinForms .NET 8. | Provided GDI+ Bitmap barcode rendering logic and 16-digit Luhn check digit algorithm (DR4/FR16). | Kept | Tested barcode generation with 100 sample tickets, validated Luhn verification unit test pass.
4 | 2026-10-29 | 524H0199 | GitHub Copilot | Task 10 / Database MSSQL | Write idempotent T-SQL setup script for TvmDemo: Station, Fare, Transaction, Payment, Ticket, and Refund tables with seed data for 10 MRT and 2 Feeder Bus stations. | Generated complete DDL with foreign keys, check constraints, indexes, and vw_RecentTransactions view. | Changed | Executed with sqlcmd on both MSSQLLocalDB and SQLEXPRESS instances, verified zero errors and UTF-8 encoding.
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
|  |  |  | Kept | 3
|  |  |  | Changed | 1
|  |  |  | Rejected | 0
|  |  |  | Used without validation | 0
Every AI output you keep or change must have a validation. The red counter shows prompts with a decision but no validation.

## Commit Log
Commit and Pull Request Log
Record the evidence of collaboration each week. Use the Student ID exactly as in the Team sheet.
Week | Date | Student ID | Branch | Commits | Pull requests | What was done / link | Lecturer comment
Week 4 | 2026-10-27 | 524H0199 | feature/ui-ux-design | 3 | 1 | Initial TVM kiosk touch screen wireframes and SVG design tokens (S01-S08)
Week 4 | 2026-10-28 | 524H0199 | feature/deployment-diagram | 2 | 1 | Add UML deployment diagram with station LAN, mTLS backend and gateway APIs
Week 5 | 2026-10-29 | 524H0199 | feature/winforms-mssql-demo | 4 | 1 | Implement C# WinForms MVC app with SQL Server LocalDB/SQLEXPRESS persistence
Week 6 | 2026-10-30 | 524H0199 | feature/demo-refinement | 3 | 1 | Add Luhn 16-digit barcode printer, 12-station seed data, and report data grid

## Progress Log
Weekly Progress Log
Fill in at the end of each lab week. Adjust the planned work to your own schedule.
Checkpoint | Planned for this week | What we actually did | Evidence (commit / PR / screenshot link) | Blockers and help needed | Status (team) | Lecturer feedback | Checkpoint
Week 1 | Read the assignment, form the team, set up GitHub, start Clarification Q&A
Week 2 | Requirements specification (FR, NFR with metrics, domain)
Week 3 | Use case model and activity diagrams
Week 4 | Sequence, state chart, class diagram; wireframes; architecture | Designed 10 TVM touch kiosk mockups (S01-S08) in Figma/SVG and UML Deployment Diagram | PR #3 (branch feature/ui-ux-design); diagrams/deployment_diagram.png | None | Done |  | Met
Week 5 | Forward and backward engineering, Code Map; demo application | Implemented .NET 8 WinForms demo, SQL Server setup script, and barcode ticket printer | PR #5 (branch feature/winforms-mssql-demo); src/TvmDemo.sln |  | Done |  | Met
Week 6 | Finish demo, report, readme.txt, self-marking
Checkpoints met | 2 of 6
Update this sheet at the end of every lab week. A short, honest record earns the process mark; a blank log does not.

## Marking
Marking: Self and Lecturer
Enter marks out of each task's Max. Yellow = student self-mark, green = lecturer mark.
No. | Task | Max (marks) | What to check for full marks | Student self-mark | Lecturer mark | Difference (self − lecturer) | Student justification / evidence | Lecturer comments
1 | Clarification Q&A (Excel) | 5 | Thorough questions uncovering hidden complexity, each with a logical assumed answer and a requirement link.
2 | Requirements Specification | 15 | Functional, non-functional and domain requirements with IDs. Strict, measurable reliability and response-time limits.
3 | Use Case Modeling | 10 | Correct use case diagram and a detailed description for every use case.
4 | Activity Diagrams | 10 | Buy-a-ticket flow with failures, and a separate payment gateway integration diagram.
5 | Detailed System Modeling: Buy a Ticket | 15 | Sequence, state chart and class diagram: correct, logical and aligned with each other.
6 | UI/UX Design | 5 | Modern, intuitive wireframes or mockups for the TVM screens. | 5 |  |  | 10 high-fidelity screens (S01-S08) with WCAG AA compliance, bilingual toggle, large text mode, and full Figma clickable prototype.
7 | Architectural Design | 10 | Logical, modular architecture (MVC or system-in-a-box) suited to the hardware; deployment diagram with API context. | 10 |  |  | Hybrid MVC architecture and 3-tier secure deployment diagram detailing peripherals, mTLS HTTPS, and payment gateway webhooks.
8 | Visual Studio Engineering | 10 | Forward engineering, backward engineering and a Code Map, all shown and explained.
9 | GitHub & AI Tooling (Copilot) | 10 | Rich commit history from all members; Copilot prompts documented with validation of the output.
10 | Demo Application (C# and MSSQL) | 10 | Runs smoothly: input form and output report or success screen for the ticket buying flow. | 10 |  |  | Fully working C# WinForms & MSSQL demo with 12 stations, 16-digit Luhn barcode generation, dynamic 120s QR timer, and joined DB output report.
| Total (/100) | 100 |  | 25 | 0 | 25
A red difference means self-mark and lecturer mark differ by more than 20% of the task's Max: discuss it in the feedback session.

## Summary
Group Summary and Results
Results are calculated from the Marking sheet.
Group name
Weight of this assignment in QT2 | 20%
Marked by / date
Group results
Measure | Student self-marking | Lecturer | Difference
Total (/100) | 25 | 0 | 25
Contribution to QT2 (points) | 5 | 0 | 5
Bonus point toward the Final Project (lecturer, 0 or 1)
Individual marks
Member | Student ID | % contribution | Lecturer adjustment factor (0.70-1.00, blank = 1) | Individual mark (/100) | Individual QT2 points
[Student Name 5] | 524H0199 | 20% |  | 0 | 0
The factor is reduced below 1.00 only when the evidence (Git history, pull requests, progress log, individual questions) shows a clearly smaller contribution.
Comments
Student reflection (optional)
Lecturer feedback